## UAR26 DRL
DRL ID | Request Type | Level | Parent DRL ID | Domain | Domain Name | Pattern | Evidence Type | Requested Item | Control Topic | Status | Status (Auto) | Priority | Date Requested | Due Date | Date Received | Date Closed | Days Open | Received Late | Extension (days) | Auditor | Auditee Owner | BU / Risk Team | Evidence Accepted | Evidence Link | IA Comments | # Follow-Ups
UAR26-PRIV-ARCH-001 | Original | Parent |  | PRIV | Privacy | ARCH | Architecture / Diagrams | Evidence request for Compliance control review | SecOps | Not Yet Requested | Not Yet Requested | Low | [5 empty] | No | 0 | Sam Auditor | Data Governance | Compliance |  |  |  | 1
UAR26-CHG-RELEASE-002 | Original | Parent |  | CHG | Change Management | RELEASE | Release and Deployment Evidence | Evidence request for Technology Risk control review | SecOps | Not Yet Requested | Not Yet Requested | Low | [5 empty] | No | 0 | Test Viewer | Platform Eng | Compliance |  |  |  | 0
UAR26-DR-RELEASE-003 | Original | Parent |  | DR | Disaster Recovery | RELEASE | Release and Deployment Evidence | Evidence request for Technology Risk control review | SecOps | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test Admin | Data Governance | Technology Risk |  |  |  | 0
UAR26-APP-SOC-004 | Original | Parent |  | APP | Application Controls | SOC | Independent Assurance Reports | Evidence request for Compliance control review | SecOps | Under IA Review | Under IA Review | High | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Lee Lead | IAM Ops | Business Risk |  |  |  | 1
UAR26-IR-EXCEPTION-005 | Original | Parent |  | IR | Incident Response | EXCEPTION | Exception, Waiver, or Risk Acceptance | Evidence request for Compliance control review | Vendor Risk | Under IA Review | Under IA Review | Low | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Lee Lead | Vendor Risk | Technology Risk |  |  |  | 1
UAR26-VM-REVIEW-006 | Original | Parent |  | VM | Vulnerability Management | REVIEW | Periodic Review Evidence | Evidence request for Business Risk control review | IAM Ops | Cancelled | Overdue | Medium | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Logan Leadership | Vendor Risk | Technology Risk |  |  |  | 0
UAR26-CHG-REVIEW-007 | Original | Parent |  | CHG | Change Management | REVIEW | Periodic Review Evidence | Evidence request for Technology Risk control review | IAM Ops | Overdue | Overdue | High | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Sam Auditor | Platform Eng | Technology Risk |  |  |  | 0
UAR26-VM-RELEASE-008 | Original | Parent |  | VM | Vulnerability Management | RELEASE | Release and Deployment Evidence | Evidence request for Business Risk control review | SecOps | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test LeadAIC | IAM Ops | Technology Risk | N |  |  | 1
UAR26-INF-INCIDENT-009 | Original | Parent |  | INF | Infrastructure | INCIDENT | Incident Evidence | Evidence request for Compliance control review | Platform Eng | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Manager | SecOps | Technology Risk | Y |  |  | 0
UAR26-CLOUD-PERF-010 | Original | Parent |  | CLOUD | Cloud Controls | PERF | Reperformance Evidence | Evidence request for Technology Risk control review | IAM Ops | Open | Open | Low | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Manager | Platform Eng | Business Risk |  |  |  | 0
UAR26-OPS-EXCEPTION-011 | Original | Parent |  | OPS | Operations | EXCEPTION | Exception, Waiver, or Risk Acceptance | Evidence request for Compliance control review | SecOps | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test LeadAIC | Vendor Risk | Technology Risk |  |  |  | 0
UAR26-OPS-SOC-012 | Original | Parent |  | OPS | Operations | SOC | Independent Assurance Reports | Evidence request for Compliance control review | IAM Ops | Extended | Extended | Low | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Lee Lead | Vendor Risk | Compliance |  |  |  | 0
UAR26-BCP-ARCH-013 | Original | Parent |  | BCP | Business Continuity | ARCH | Architecture / Diagrams | Evidence request for Compliance control review | Data Governance | Not Yet Requested | Not Yet Requested | Medium | [5 empty] | No | 0 | Test Viewer | Platform Eng | Technology Risk |  |  |  | 0
UAR26-CLOUD-DOC-014 | Original | Parent |  | CLOUD | Cloud Controls | DOC | Policies / Procedures / Standards | Evidence request for Compliance control review | SecOps | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Admin | Platform Eng | Technology Risk | Y |  |  | 0
UAR26-PRIV-TRAN-015 | Original | Parent |  | PRIV | Privacy | TRAN | Transaction Support Evidence | Evidence request for Business Risk control review | Vendor Risk | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Lee Lead | IAM Ops | Technology Risk |  |  |  | 1
UAR26-CLOUD-SOC-016 | Original | Parent |  | CLOUD | Cloud Controls | SOC | Independent Assurance Reports | Evidence request for Compliance control review | SecOps | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Logan Leadership | Platform Eng | Compliance |  |  |  | 0
UAR26-PRIV-CONFIG-017 | Original | Parent |  | PRIV | Privacy | CONFIG | Configuration Population | Evidence request for Business Risk control review | Vendor Risk | Cancelled | Overdue | High | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Viewer | Data Governance | Technology Risk |  |  |  | 0
UAR26-VM-DOC-018 | Original | Parent |  | VM | Vulnerability Management | DOC | Policies / Procedures / Standards | Evidence request for Compliance control review | Data Governance | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Logan Leadership | Platform Eng | Business Risk | N |  |  | 0
UAR26-CLOUD-EXCEPTION-019 | Original | Parent |  | CLOUD | Cloud Controls | EXCEPTION | Exception, Waiver, or Risk Acceptance | Evidence request for Compliance control review | IAM Ops | Extended | Extended | Medium | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Logan Leadership | Platform Eng | Business Risk |  |  |  | 0
UAR26-PRIV-PERF-020 | Original | Parent |  | PRIV | Privacy | PERF | Reperformance Evidence | Evidence request for Compliance control review | SecOps | Open | Open | Low | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Viewer | Vendor Risk | Technology Risk |  |  |  | 1
UAR26-PRIV-REVIEW-021 | Original | Parent |  | PRIV | Privacy | REVIEW | Periodic Review Evidence | Evidence request for Technology Risk control review | SecOps | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Val Viewer | Vendor Risk | Business Risk |  |  |  | 1
UAR26-GOV-RELEASE-022 | Original | Parent |  | GOV | Governance | RELEASE | Release and Deployment Evidence | Evidence request for Technology Risk control review | Data Governance | Under IA Review | Under IA Review | High | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Manager | Data Governance | Business Risk |  |  |  | 1
UAR26-DR-REMED-023 | Original | Parent |  | DR | Disaster Recovery | REMED | Remediation / Issue Tracking | Evidence request for Compliance control review | Platform Eng | Overdue | Overdue | Medium | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Viewer | IAM Ops | Compliance |  |  |  | 0
UAR26-AC-DATAFLOW-024 | Original | Parent |  | AC | Access Control | DATAFLOW | Data Flow Evidence | Evidence request for Technology Risk control review | Data Governance | Not Yet Requested | Not Yet Requested | Low | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Morgan Manager | Data Governance | Compliance |  |  |  | 0
UAR26-OPS-DATAFLOW-025 | Original | Parent |  | OPS | Operations | DATAFLOW | Data Flow Evidence | Evidence request for Business Risk control review | IAM Ops | Extended | Extended | Medium | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Auditor | Data Governance | Compliance |  |  |  | 1
UAR26-AC-CONTRACT-026 | Original | Parent |  | AC | Access Control | CONTRACT | Contractual Documentation | Evidence request for Compliance control review | SecOps | Not Yet Requested | Not Yet Requested | Low | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Sam Auditor | IAM Ops | Business Risk |  |  |  | 0
UAR26-DATA-LOG-027 | Original | Parent |  | DATA | Data Management | LOG | Logs / Monitoring Evidence | Evidence request for Compliance control review | Data Governance | Open | Open | Medium | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Admin | Platform Eng | Technology Risk |  |  |  | 1
UAR26-PRIV-TICKET-028 | Original | Parent |  | PRIV | Privacy | TICKET | Workflow / Ticket Evidence | Evidence request for Technology Risk control review | Data Governance | Overdue | Overdue | Low | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Viewer | IAM Ops | Compliance |  |  |  | 0
UAR26-GOV-ASSESS-029 | Original | Parent |  | GOV | Governance | ASSESS | Assessment Results | Evidence request for Compliance control review | SecOps | Cancelled | Overdue | Medium | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Admin | Platform Eng | Technology Risk |  |  |  | 1
UAR26-DATA-MONITOR-030 | Original | Parent |  | DATA | Data Management | MONITOR | Monitoring Activities | Evidence request for Business Risk control review | SecOps | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Auditor | Data Governance | Technology Risk | N |  |  | 0
UAR26-BCP-ASSESS-031 | Original | Parent |  | BCP | Business Continuity | ASSESS | Assessment Results | Evidence request for Business Risk control review | Vendor Risk | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Test Viewer | SecOps | Business Risk |  |  |  | 0
UAR26-DATA-DOC-032 | Original | Parent |  | DATA | Data Management | DOC | Policies / Procedures / Standards | Evidence request for Business Risk control review | IAM Ops | Closed - Complete | Closed - Complete | Low | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Manager | Data Governance | Business Risk | Y |  |  | 1
UAR26-AC-INCIDENT-033 | Original | Parent |  | AC | Access Control | INCIDENT | Incident Evidence | Evidence request for Compliance control review | Vendor Risk | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Admin | IAM Ops | Technology Risk |  |  |  | 0
UAR26-CHG-RACI-034 | Original | Parent |  | CHG | Change Management | RACI | Roles and Responsibilities | Evidence request for Compliance control review | Platform Eng | Under IA Review | Under IA Review | Medium | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Admin | Data Governance | Business Risk |  |  |  | 0
UAR26-INF-TICKET-035 | Original | Parent |  | INF | Infrastructure | TICKET | Workflow / Ticket Evidence | Evidence request for Compliance control review | IAM Ops | Overdue - Extension | Overdue - Extension | Medium | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test Manager | Platform Eng | Technology Risk |  |  |  | 0
UAR26-DR-CHANGE-036 | Original | Parent |  | DR | Disaster Recovery | CHANGE | Change Population | Evidence request for Business Risk control review | Vendor Risk | Open | Open | High | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test LeadAIC | Platform Eng | Compliance |  |  |  | 1
UAR26-OPS-SAMPLE-037 | Original | Parent |  | OPS | Operations | SAMPLE | Sample Selection Evidence | Evidence request for Compliance control review | Vendor Risk | Open | Open | Low | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Lee Lead | SecOps | Business Risk |  |  |  | 0
UAR26-AI-ATTEST-038 | Original | Parent |  | AI | Artificial Intelligence | ATTEST | Management Attestation / Certification | Evidence request for Compliance control review | Platform Eng | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Admin | IAM Ops | Business Risk |  |  |  | 0
UAR26-IR-CHANGE-039 | Original | Parent |  | IR | Incident Response | CHANGE | Change Population | Evidence request for Technology Risk control review | SecOps | Under IA Review | Under IA Review | Medium | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Sam Auditor | Vendor Risk | Business Risk |  |  |  | 1
UAR26-PRIV-INVENT-040 | Original | Parent |  | PRIV | Privacy | INVENT | Asset or Account Inventory | Evidence request for Technology Risk control review | SecOps | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Auditor | Data Governance | Business Risk | Y |  |  | 1
UAR26-AI-TEST-041 | Original | Parent |  | AI | Artificial Intelligence | TEST | Testing Evidence | Evidence request for Technology Risk control review | Data Governance | Not Yet Requested | Not Yet Requested | Low | [5 empty] | No | 0 | Test Manager | SecOps | Technology Risk |  |  |  | 0
UAR26-VEND-TEST-042 | Original | Parent |  | VEND | Third-Party Risk | TEST | Testing Evidence | Evidence request for Business Risk control review | IAM Ops | Overdue | Overdue | Medium | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Manager | Data Governance | Business Risk |  |  |  | 1
UAR26-CHG-CONFIGTEST-043 | Original | Parent |  | CHG | Change Management | CONFIGTEST | Configuration Validation Evidence | Evidence request for Business Risk control review | Vendor Risk | Extended | Extended | Low | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Logan Leadership | SecOps | Technology Risk |  |  |  | 0
UAR26-INF-APPROVAL-044 | Original | Parent |  | INF | Infrastructure | APPROVAL | Access / Change Approval Evidence | Evidence request for Technology Risk control review | SecOps | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Logan Leadership | IAM Ops | Business Risk |  |  |  | 0
UAR26-INF-RELEASE-045 | Original | Parent |  | INF | Infrastructure | RELEASE | Release and Deployment Evidence | Evidence request for Business Risk control review | SecOps | Cancelled | Overdue | High | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Viewer | Platform Eng | Compliance |  |  |  | 0
UAR26-CHG-RELEASE-046 | Original | Parent |  | CHG | Change Management | RELEASE | Release and Deployment Evidence | Evidence request for Business Risk control review | Data Governance | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Logan Leadership | Data Governance | Compliance |  |  |  | 0
UAR26-DATA-LIST-047 | Original | Parent |  | DATA | Data Management | LIST | System-Generated Population Listing | Evidence request for Business Risk control review | Data Governance | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test LeadAIC | SecOps | Compliance | N |  |  | 1
UAR26-CHG-CHANGE-048 | Original | Parent |  | CHG | Change Management | CHANGE | Change Population | Evidence request for Technology Risk control review | Vendor Risk | Overdue | Overdue | High | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Leadership | Vendor Risk | Compliance |  |  |  | 1
UAR26-VEND-CONFIG-049 | Original | Parent |  | VEND | Third-Party Risk | CONFIG | Configuration Population | Evidence request for Technology Risk control review | IAM Ops | Under IA Review | Under IA Review | Low | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Manager | Platform Eng | Compliance |  |  |  | 0
UAR26-OPS-TEST-050 | Original | Parent |  | OPS | Operations | TEST | Testing Evidence | Evidence request for Technology Risk control review | Vendor Risk | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test Admin | Data Governance | Technology Risk |  |  |  | 1
UAR26-OPS-INCIDENT-051 | Original | Parent |  | OPS | Operations | INCIDENT | Incident Evidence | Evidence request for Compliance control review | Data Governance | Closed - Complete | Closed - Complete | Low | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Morgan Manager | Vendor Risk | Compliance | N |  |  | 0
UAR26-DATA-ARCH-052 | Original | Parent |  | DATA | Data Management | ARCH | Architecture / Diagrams | Evidence request for Business Risk control review | SecOps | Extended | Extended | High | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Sam Auditor | Platform Eng | Compliance |  |  |  | 0
UAR26-DR-ATTEST-053 | Original | Parent |  | DR | Disaster Recovery | ATTEST | Management Attestation / Certification | Evidence request for Technology Risk control review | Data Governance | Cancelled | Overdue | High | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test LeadAIC | Platform Eng | Technology Risk |  |  |  | 0
UAR26-CHG-INCIDENT-054 | Original | Parent |  | CHG | Change Management | INCIDENT | Incident Evidence | Evidence request for Compliance control review | Data Governance | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Viewer | Vendor Risk | Compliance |  |  |  | 1
UAR26-AI-RELEASE-055 | Original | Parent |  | AI | Artificial Intelligence | RELEASE | Release and Deployment Evidence | Evidence request for Business Risk control review | Data Governance | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Auditor | Platform Eng | Compliance | Y |  |  | 0
UAR26-PRIV-REVIEW-021.1 | Follow-Up | Child | UAR26-PRIV-REVIEW-021 |  |  |  | Periodic Review Evidence | Follow-up on the original submission |  | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Avery Admin | [5 empty] | 0
UAR26-IR-CHANGE-039.1 | Remediation | Child | UAR26-IR-CHANGE-039 |  |  |  | Change Population | Follow-up on the original submission |  | Overdue | Overdue | Low | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Admin | [5 empty] | 0
UAR26-IR-EXCEPTION-005.1 | Follow-Up | Child | UAR26-IR-EXCEPTION-005 |  |  |  | Exception, Waiver, or Risk Acceptance | Follow-up on the original submission |  | Open | Open | Medium | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Auditor | [5 empty] | 0
UAR26-PRIV-INVENT-040.1 | Follow-Up | Child | UAR26-PRIV-INVENT-040 |  |  |  | Asset or Account Inventory | Follow-up on the original submission |  | Extended | Extended | High | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Viewer | [5 empty] | 0
UAR26-PRIV-ARCH-001.1 | Clarification | Child | UAR26-PRIV-ARCH-001 |  |  |  | Architecture / Diagrams | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Logan Leadership | [5 empty] | 0
UAR26-DATA-LOG-027.1 | Follow-Up | Child | UAR26-DATA-LOG-027 |  |  |  | Logs / Monitoring Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Auditor |  |  | Y |  |  | 0
UAR26-CHG-CHANGE-048.1 | Remediation | Child | UAR26-CHG-CHANGE-048 |  |  |  | Change Population | Follow-up on the original submission |  | Under IA Review | Under IA Review | High | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Admin | [5 empty] | 0
UAR26-APP-SOC-004.1 | Clarification | Child | UAR26-APP-SOC-004 |  |  |  | Independent Assurance Reports | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Sam Auditor | [5 empty] | 0
UAR26-PRIV-PERF-020.1 | Clarification | Child | UAR26-PRIV-PERF-020 |  |  |  | Reperformance Evidence | Follow-up on the original submission |  | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test Admin | [5 empty] | 0
UAR26-OPS-TEST-050.1 | Follow-Up | Child | UAR26-OPS-TEST-050 |  |  |  | Testing Evidence | Follow-up on the original submission |  | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Admin | [5 empty] | 0
UAR26-GOV-ASSESS-029.1 | Clarification | Child | UAR26-GOV-ASSESS-029 |  |  |  | Assessment Results | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | Low | [5 empty] | No | 0 | Test LeadAIC | [5 empty] | 0
UAR26-GOV-RELEASE-022.1 | Remediation | Child | UAR26-GOV-RELEASE-022 |  |  |  | Release and Deployment Evidence | Follow-up on the original submission |  | Under IA Review | Under IA Review | High | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Val Viewer | [5 empty] | 0
UAR26-CHG-INCIDENT-054.1 | Follow-Up | Child | UAR26-CHG-INCIDENT-054 |  |  |  | Incident Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Avery Admin |  |  | Y |  |  | 0
UAR26-OPS-DATAFLOW-025.1 | Remediation | Child | UAR26-OPS-DATAFLOW-025 |  |  |  | Data Flow Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Logan Leadership |  |  | N |  |  | 0
UAR26-DATA-LIST-047.1 | Remediation | Child | UAR26-DATA-LIST-047 |  |  |  | System-Generated Population Listing | Follow-up on the original submission |  | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test Auditor | [5 empty] | 0
UAR26-VM-RELEASE-008.1 | Remediation | Child | UAR26-VM-RELEASE-008 |  |  |  | Release and Deployment Evidence | Follow-up on the original submission |  | Overdue | Overdue | High | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Logan Leadership | [5 empty] | 0
UAR26-VEND-TEST-042.1 | Follow-Up | Child | UAR26-VEND-TEST-042 |  |  |  | Testing Evidence | Follow-up on the original submission |  | Open | Open | High | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Manager | [5 empty] | 0
UAR26-PRIV-TRAN-015.1 | Remediation | Child | UAR26-PRIV-TRAN-015 |  |  |  | Transaction Support Evidence | Follow-up on the original submission |  | Extended | Extended | Low | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Avery Admin | [5 empty] | 0
UAR26-DATA-DOC-032.1 | Clarification | Child | UAR26-DATA-DOC-032 |  |  |  | Policies / Procedures / Standards | Follow-up on the original submission |  | Cancelled | Overdue | Medium | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Sam Auditor | [5 empty] | 0
UAR26-DR-CHANGE-036.1 | Clarification | Child | UAR26-DR-CHANGE-036 |  |  |  | Change Population | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | Medium | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Logan Leadership | [5 empty] | 0