## CHG26 DRL
DRL ID | Request Type | Level | Parent DRL ID | Domain | Domain Name | Pattern | Evidence Type | Requested Item | Control Topic | Status | Status (Auto) | Priority | Date Requested | Due Date | Date Received | Date Closed | Days Open | Received Late | Extension (days) | Auditor | Auditee Owner | BU / Risk Team | Evidence Accepted | Evidence Link | IA Comments | # Follow-Ups
CHG26-IR-ISSUE-001 | Original | Parent |  | IR | Incident Response | ISSUE | Issue Management Evidence | Evidence request for Compliance control review | SecOps | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Test LeadAIC | IAM Ops | Business Risk |  |  |  | 0
CHG26-BCP-LIST-002 | Original | Parent |  | BCP | Business Continuity | LIST | System-Generated Population Listing | Evidence request for Compliance control review | Data Governance | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Test Manager | Vendor Risk | Technology Risk |  |  |  | 1
CHG26-CLOUD-EXCEPTION-003 | Original | Parent |  | CLOUD | Cloud Controls | EXCEPTION | Exception, Waiver, or Risk Acceptance | Evidence request for Business Risk control review | Platform Eng | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Morgan Manager | SecOps | Business Risk | Y |  |  | 1
CHG26-VM-CONFIG-004 | Original | Parent |  | VM | Vulnerability Management | CONFIG | Configuration Population | Evidence request for Business Risk control review | Vendor Risk | Overdue | Overdue | Low | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Avery Admin | IAM Ops | Business Risk |  |  |  | 1
CHG26-APP-SOC-005 | Original | Parent |  | APP | Application Controls | SOC | Independent Assurance Reports | Evidence request for Technology Risk control review | Vendor Risk | Open | Open | Low | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Admin | Data Governance | Business Risk |  |  |  | 0
CHG26-IR-APPROVAL-006 | Original | Parent |  | IR | Incident Response | APPROVAL | Access / Change Approval Evidence | Evidence request for Compliance control review | IAM Ops | Overdue - Extension | Overdue - Extension | Medium | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Avery Admin | IAM Ops | Business Risk |  |  |  | 0
CHG26-APP-SAMPLE-007 | Original | Parent |  | APP | Application Controls | SAMPLE | Sample Selection Evidence | Evidence request for Technology Risk control review | Vendor Risk | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test LeadAIC | SecOps | Technology Risk |  |  |  | 0
CHG26-GOV-CONFIG-008 | Original | Parent |  | GOV | Governance | CONFIG | Configuration Population | Evidence request for Business Risk control review | Vendor Risk | Extended | Extended | Medium | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Morgan Manager | Platform Eng | Compliance |  |  |  | 1
CHG26-IR-SAMPLE-009 | Original | Parent |  | IR | Incident Response | SAMPLE | Sample Selection Evidence | Evidence request for Technology Risk control review | Platform Eng | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Lee Lead | IAM Ops | Compliance | N |  |  | 1
CHG26-VEND-INVENT-010 | Original | Parent |  | VEND | Third-Party Risk | INVENT | Asset or Account Inventory | Evidence request for Compliance control review | Platform Eng | Cancelled | Overdue | Medium | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Viewer | IAM Ops | Business Risk |  |  |  | 0
CHG26-APP-REMED-011 | Original | Parent |  | APP | Application Controls | REMED | Remediation / Issue Tracking | Evidence request for Compliance control review | Platform Eng | Under IA Review | Under IA Review | Medium | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Admin | SecOps | Compliance |  |  |  | 1
CHG26-IR-CONFIG-012 | Original | Parent |  | IR | Incident Response | CONFIG | Configuration Population | Evidence request for Technology Risk control review | IAM Ops | Under IA Review | Under IA Review | Low | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Admin | IAM Ops | Technology Risk |  |  |  | 0
CHG26-DR-RACI-013 | Original | Parent |  | DR | Disaster Recovery | RACI | Roles and Responsibilities | Evidence request for Compliance control review | Platform Eng | Not Yet Requested | Not Yet Requested | Low | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Sam Auditor | Vendor Risk | Technology Risk |  |  |  | 0
CHG26-DR-INVENT-014 | Original | Parent |  | DR | Disaster Recovery | INVENT | Asset or Account Inventory | Evidence request for Technology Risk control review | Vendor Risk | Not Yet Requested | Not Yet Requested | Medium | [5 empty] | No | 0 | Test LeadAIC | Platform Eng | Compliance |  |  |  | 0
CHG26-CHG-INCIDENT-015 | Original | Parent |  | CHG | Change Management | INCIDENT | Incident Evidence | Evidence request for Technology Risk control review | Vendor Risk | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Morgan Manager | Platform Eng | Compliance | N |  |  | 0
CHG26-CLOUD-CONTRACT-016 | Original | Parent |  | CLOUD | Cloud Controls | CONTRACT | Contractual Documentation | Evidence request for Compliance control review | SecOps | Under IA Review | Under IA Review | Medium | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Viewer | Vendor Risk | Compliance |  |  |  | 0
CHG26-DR-LIST-017 | Original | Parent |  | DR | Disaster Recovery | LIST | System-Generated Population Listing | Evidence request for Compliance control review | Vendor Risk | Under IA Review | Under IA Review | Low | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Logan Leadership | Platform Eng | Technology Risk |  |  |  | 0
CHG26-DR-ASSESS-018 | Original | Parent |  | DR | Disaster Recovery | ASSESS | Assessment Results | Evidence request for Technology Risk control review | SecOps | Extended | Extended | High | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Leadership | IAM Ops | Technology Risk |  |  |  | 0
CHG26-DR-RACI-019 | Original | Parent |  | DR | Disaster Recovery | RACI | Roles and Responsibilities | Evidence request for Business Risk control review | Data Governance | Overdue - Extension | Overdue - Extension | Medium | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test LeadAIC | SecOps | Technology Risk |  |  |  | 1
CHG26-CHG-REVIEW-020 | Original | Parent |  | CHG | Change Management | REVIEW | Periodic Review Evidence | Evidence request for Technology Risk control review | Platform Eng | Cancelled | Overdue | Low | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Morgan Manager | Platform Eng | Compliance |  |  |  | 1
CHG26-INF-RELEASE-021 | Original | Parent |  | INF | Infrastructure | RELEASE | Release and Deployment Evidence | Evidence request for Business Risk control review | IAM Ops | Open | Open | High | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Sam Auditor | Data Governance | Technology Risk |  |  |  | 0
CHG26-SEC-DATAFLOW-022 | Original | Parent |  | SEC | Security | DATAFLOW | Data Flow Evidence | Evidence request for Technology Risk control review | SecOps | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Leadership | Vendor Risk | Technology Risk | Y |  |  | 0
CHG26-PRIV-CONFIG-023 | Original | Parent |  | PRIV | Privacy | CONFIG | Configuration Population | Evidence request for Technology Risk control review | Vendor Risk | Overdue | Overdue | High | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Avery Admin | Platform Eng | Business Risk |  |  |  | 1
CHG26-VEND-LIST-024 | Original | Parent |  | VEND | Third-Party Risk | LIST | System-Generated Population Listing | Evidence request for Technology Risk control review | IAM Ops | Not Yet Requested | Not Yet Requested | Low | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test Leadership | SecOps | Compliance |  |  |  | 0
CHG26-CLOUD-SOC-025 | Original | Parent |  | CLOUD | Cloud Controls | SOC | Independent Assurance Reports | Evidence request for Business Risk control review | Data Governance | Cancelled | Overdue | Low | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Admin | SecOps | Compliance |  |  |  | 0
CHG26-CHG-SAMPLE-026 | Original | Parent |  | CHG | Change Management | SAMPLE | Sample Selection Evidence | Evidence request for Compliance control review | IAM Ops | Overdue - Extension | Overdue - Extension | Medium | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test Admin | Platform Eng | Technology Risk |  |  |  | 0
CHG26-BCP-LOG-027 | Original | Parent |  | BCP | Business Continuity | LOG | Logs / Monitoring Evidence | Evidence request for Compliance control review | Platform Eng | Not Yet Requested | Not Yet Requested | Medium | [5 empty] | No | 0 | Morgan Manager | Platform Eng | Technology Risk |  |  |  | 1
CHG26-BCP-TRAIN-028 | Original | Parent |  | BCP | Business Continuity | TRAIN | Training Evidence | Evidence request for Technology Risk control review | IAM Ops | Under IA Review | Under IA Review | High | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Morgan Manager | SecOps | Compliance |  |  |  | 0
CHG26-DR-CONFIGTEST-029 | Original | Parent |  | DR | Disaster Recovery | CONFIGTEST | Configuration Validation Evidence | Evidence request for Technology Risk control review | Data Governance | Open | Open | Low | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Lee Lead | IAM Ops | Technology Risk |  |  |  | 1
CHG26-AC-INVENT-030 | Original | Parent |  | AC | Access Control | INVENT | Asset or Account Inventory | Evidence request for Technology Risk control review | SecOps | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Morgan Manager | Data Governance | Business Risk | N |  |  | 0
CHG26-DR-DATAFLOW-031 | Original | Parent |  | DR | Disaster Recovery | DATAFLOW | Data Flow Evidence | Evidence request for Compliance control review | Platform Eng | Overdue | Overdue | Medium | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Val Viewer | IAM Ops | Business Risk |  |  |  | 1
CHG26-IR-TEST-032 | Original | Parent |  | IR | Incident Response | TEST | Testing Evidence | Evidence request for Technology Risk control review | Vendor Risk | Not Yet Requested | Not Yet Requested | Low | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Morgan Manager | IAM Ops | Business Risk |  |  |  | 0
CHG26-BCP-LIST-033 | Original | Parent |  | BCP | Business Continuity | LIST | System-Generated Population Listing | Evidence request for Business Risk control review | Vendor Risk | Extended | Extended | High | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Auditor | SecOps | Technology Risk |  |  |  | 0
CHG26-GOV-APPROVAL-034 | Original | Parent |  | GOV | Governance | APPROVAL | Access / Change Approval Evidence | Evidence request for Business Risk control review | Vendor Risk | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Val Viewer | Data Governance | Compliance |  |  |  | 1
CHG26-AI-ASSESS-035 | Original | Parent |  | AI | Artificial Intelligence | ASSESS | Assessment Results | Evidence request for Technology Risk control review | IAM Ops | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Avery Admin | IAM Ops | Technology Risk | Y |  |  | 1
CHG26-INF-RELEASE-036 | Original | Parent |  | INF | Infrastructure | RELEASE | Release and Deployment Evidence | Evidence request for Technology Risk control review | Vendor Risk | Open | Open | High | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Viewer | Platform Eng | Technology Risk |  |  |  | 0
CHG26-DR-MONITOR-037 | Original | Parent |  | DR | Disaster Recovery | MONITOR | Monitoring Activities | Evidence request for Technology Risk control review | Platform Eng | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Avery Admin | IAM Ops | Business Risk |  |  |  | 0
CHG26-GOV-LIST-038 | Original | Parent |  | GOV | Governance | LIST | System-Generated Population Listing | Evidence request for Technology Risk control review | IAM Ops | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Sam Auditor | SecOps | Technology Risk | Y |  |  | 1
CHG26-VM-TICKET-039 | Original | Parent |  | VM | Vulnerability Management | TICKET | Workflow / Ticket Evidence | Evidence request for Business Risk control review | Platform Eng | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Admin | Vendor Risk | Technology Risk | N |  |  | 0
CHG26-CHG-MONITOR-040 | Original | Parent |  | CHG | Change Management | MONITOR | Monitoring Activities | Evidence request for Business Risk control review | Data Governance | Overdue | Overdue | High | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Auditor | Platform Eng | Compliance |  |  |  | 0
CHG26-AI-TRAIN-041 | Original | Parent |  | AI | Artificial Intelligence | TRAIN | Training Evidence | Evidence request for Compliance control review | SecOps | Under IA Review | Under IA Review | Low | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Lee Lead | Vendor Risk | Compliance |  |  |  | 1
CHG26-BCP-PERF-042 | Original | Parent |  | BCP | Business Continuity | PERF | Reperformance Evidence | Evidence request for Compliance control review | Platform Eng | Not Yet Requested | Not Yet Requested | Low | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test LeadAIC | Platform Eng | Technology Risk |  |  |  | 1
CHG26-VEND-EXCEPTION-043 | Original | Parent |  | VEND | Third-Party Risk | EXCEPTION | Exception, Waiver, or Risk Acceptance | Evidence request for Compliance control review | IAM Ops | Extended | Extended | Medium | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Admin | SecOps | Business Risk |  |  |  | 1
CHG26-VEND-REMED-044 | Original | Parent |  | VEND | Third-Party Risk | REMED | Remediation / Issue Tracking | Evidence request for Technology Risk control review | Data Governance | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test Auditor | SecOps | Compliance |  |  |  | 1
CHG26-BCP-CONTRACT-045 | Original | Parent |  | BCP | Business Continuity | CONTRACT | Contractual Documentation | Evidence request for Compliance control review | SecOps | Cancelled | Overdue | Medium | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Viewer | Vendor Risk | Technology Risk |  |  |  | 0
CHG26-INF-SOC-046 | Original | Parent |  | INF | Infrastructure | SOC | Independent Assurance Reports | Evidence request for Business Risk control review | SecOps | Under IA Review | Under IA Review | High | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Avery Admin | Data Governance | Compliance |  |  |  | 1
CHG26-GOV-LIST-047 | Original | Parent |  | GOV | Governance | LIST | System-Generated Population Listing | Evidence request for Business Risk control review | IAM Ops | Open | Open | Low | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test LeadAIC | Vendor Risk | Business Risk |  |  |  | 1
CHG26-GOV-CONFIG-048 | Original | Parent |  | GOV | Governance | CONFIG | Configuration Population | Evidence request for Business Risk control review | IAM Ops | Overdue | Overdue | Medium | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Auditor | Vendor Risk | Business Risk |  |  |  | 1
CHG26-BCP-LOG-049 | Original | Parent |  | BCP | Business Continuity | LOG | Logs / Monitoring Evidence | Evidence request for Technology Risk control review | Data Governance | Under IA Review | Under IA Review | Medium | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Admin | Platform Eng | Business Risk |  |  |  | 0
CHG26-AI-REMED-050 | Original | Parent |  | AI | Artificial Intelligence | REMED | Remediation / Issue Tracking | Evidence request for Technology Risk control review | Platform Eng | Extended | Extended | High | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Leadership | Vendor Risk | Compliance |  |  |  | 0
CHG26-PRIV-LOG-051 | Original | Parent |  | PRIV | Privacy | LOG | Logs / Monitoring Evidence | Evidence request for Compliance control review | Vendor Risk | Overdue - Extension | Overdue - Extension | Low | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Lee Lead | IAM Ops | Technology Risk |  |  |  | 0
CHG26-SEC-TEST-052 | Original | Parent |  | SEC | Security | TEST | Testing Evidence | Evidence request for Business Risk control review | Data Governance | Cancelled | Overdue | Low | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Sam Auditor | SecOps | Compliance |  |  |  | 0
CHG26-INF-SAMPLE-053 | Original | Parent |  | INF | Infrastructure | SAMPLE | Sample Selection Evidence | Evidence request for Compliance control review | Data Governance | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Avery Admin | Vendor Risk | Compliance | Y |  |  | 0
CHG26-INF-DATAFLOW-054 | Original | Parent |  | INF | Infrastructure | DATAFLOW | Data Flow Evidence | Evidence request for Technology Risk control review | Vendor Risk | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Auditor | Data Governance | Compliance | N |  |  | 0
CHG26-CHG-INVENT-055 | Original | Parent |  | CHG | Change Management | INVENT | Asset or Account Inventory | Evidence request for Technology Risk control review | Platform Eng | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Manager | Vendor Risk | Business Risk |  |  |  | 1
CHG26-PRIV-CONFIG-023.1 | Remediation | Child | CHG26-PRIV-CONFIG-023 |  |  |  | Configuration Population | Follow-up on the original submission |  | Under IA Review | Under IA Review | High | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Viewer | [5 empty] | 0
CHG26-CLOUD-EXCEPTION-003.1 | Clarification | Child | CHG26-CLOUD-EXCEPTION-003 |  |  |  | Exception, Waiver, or Risk Acceptance | Follow-up on the original submission |  | Overdue | Overdue | High | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Lee Lead | [5 empty] | 0
CHG26-GOV-LIST-038.1 | Follow-Up | Child | CHG26-GOV-LIST-038 |  |  |  | System-Generated Population Listing | Follow-up on the original submission |  | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Lee Lead | [5 empty] | 0
CHG26-DR-DATAFLOW-031.1 | Follow-Up | Child | CHG26-DR-DATAFLOW-031 |  |  |  | Data Flow Evidence | Follow-up on the original submission |  | Cancelled | Overdue | High | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Leadership | [5 empty] | 0
CHG26-AI-ASSESS-035.1 | Remediation | Child | CHG26-AI-ASSESS-035 |  |  |  | Assessment Results | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Logan Leadership | [5 empty] | 0
CHG26-VEND-REMED-044.1 | Remediation | Child | CHG26-VEND-REMED-044 |  |  |  | Remediation / Issue Tracking | Follow-up on the original submission |  | Extended | Extended | Medium | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Sam Auditor | [5 empty] | 0
CHG26-GOV-APPROVAL-034.1 | Follow-Up | Child | CHG26-GOV-APPROVAL-034 |  |  |  | Access / Change Approval Evidence | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | Low | [5 empty] | No | 0 | Test Manager | [5 empty] | 0
CHG26-APP-REMED-011.1 | Remediation | Child | CHG26-APP-REMED-011 |  |  |  | Remediation / Issue Tracking | Follow-up on the original submission |  | Open | Open | Low | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test LeadAIC | [5 empty] | 0
CHG26-BCP-PERF-042.1 | Clarification | Child | CHG26-BCP-PERF-042 |  |  |  | Reperformance Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Leadership |  |  | Y |  |  | 0
CHG26-VM-CONFIG-004.1 | Remediation | Child | CHG26-VM-CONFIG-004 |  |  |  | Configuration Population | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | Medium | [5 empty] | No | 0 | Morgan Manager | [5 empty] | 0
CHG26-INF-SOC-046.1 | Remediation | Child | CHG26-INF-SOC-046 |  |  |  | Independent Assurance Reports | Follow-up on the original submission |  | Under IA Review | Under IA Review | High | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Morgan Manager | [5 empty] | 0
CHG26-DR-CONFIGTEST-029.1 | Follow-Up | Child | CHG26-DR-CONFIGTEST-029 |  |  |  | Configuration Validation Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Val Viewer |  |  | N |  |  | 0
CHG26-BCP-LOG-027.1 | Remediation | Child | CHG26-BCP-LOG-027 |  |  |  | Logs / Monitoring Evidence | Follow-up on the original submission |  | Open | Open | Medium | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Auditor | [5 empty] | 0
CHG26-IR-SAMPLE-009.1 | Remediation | Child | CHG26-IR-SAMPLE-009 |  |  |  | Sample Selection Evidence | Follow-up on the original submission |  | Extended | Extended | Medium | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Morgan Manager | [5 empty] | 0
CHG26-AI-TRAIN-041.1 | Follow-Up | Child | CHG26-AI-TRAIN-041 |  |  |  | Training Evidence | Follow-up on the original submission |  | Overdue - Extension | Overdue - Extension | Medium | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Lee Lead | [5 empty] | 0
CHG26-CHG-REVIEW-020.1 | Clarification | Child | CHG26-CHG-REVIEW-020 |  |  |  | Periodic Review Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | Low | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Manager |  |  | Y |  |  | 0
CHG26-GOV-CONFIG-048.1 | Remediation | Child | CHG26-GOV-CONFIG-048 |  |  |  | Configuration Population | Follow-up on the original submission |  | Cancelled | Overdue | Low | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Logan Leadership | [5 empty] | 0
CHG26-BCP-LIST-002.1 | Follow-Up | Child | CHG26-BCP-LIST-002 |  |  |  | System-Generated Population Listing | Follow-up on the original submission |  | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test Viewer | [5 empty] | 0
CHG26-CHG-INVENT-055.1 | Remediation | Child | CHG26-CHG-INVENT-055 |  |  |  | Asset or Account Inventory | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Avery Admin | [5 empty] | 0
CHG26-DR-RACI-019.1 | Clarification | Child | CHG26-DR-RACI-019 |  |  |  | Roles and Responsibilities | Follow-up on the original submission |  | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Auditor | [5 empty] | 0
CHG26-GOV-LIST-047.1 | Remediation | Child | CHG26-GOV-LIST-047 |  |  |  | System-Generated Population Listing | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Admin |  |  | N |  |  | 0
CHG26-GOV-CONFIG-008.1 | Clarification | Child | CHG26-GOV-CONFIG-008 |  |  |  | Configuration Population | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | Low | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Val Viewer | [5 empty] | 0
CHG26-VEND-EXCEPTION-043.1 | Follow-Up | Child | CHG26-VEND-EXCEPTION-043 |  |  |  | Exception, Waiver, or Risk Acceptance | Follow-up on the original submission |  | Overdue | Overdue | Low | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Val Viewer | [5 empty] | 0