## ITOPS26 DRL
DRL ID | Request Type | Level | Parent DRL ID | Domain | Domain Name | Pattern | Evidence Type | Requested Item | Control Topic | Status | Status (Auto) | Priority | Date Requested | Due Date | Date Received | Date Closed | Days Open | Received Late | Extension (days) | Auditor | Auditee Owner | BU / Risk Team | Evidence Accepted | Evidence Link | IA Comments | # Follow-Ups
ITOPS26-CLOUD-INVENT-001 | Original | Parent |  | CLOUD | Cloud Controls | INVENT | Asset or Account Inventory | Evidence request for Compliance control review | Data Governance | Not Yet Requested | Not Yet Requested | Low | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test Manager | Data Governance | Technology Risk |  |  |  | 0
ITOPS26-DATA-ASSESS-002 | Original | Parent |  | DATA | Data Management | ASSESS | Assessment Results | Evidence request for Technology Risk control review | IAM Ops | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Test Viewer | SecOps | Business Risk |  |  |  | 0
ITOPS26-AC-TRAN-003 | Original | Parent |  | AC | Access Control | TRAN | Transaction Support Evidence | Evidence request for Technology Risk control review | Platform Eng | Cancelled | Overdue | High | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Leadership | SecOps | Technology Risk |  |  |  | 0
ITOPS26-VEND-RELEASE-004 | Original | Parent |  | VEND | Third-Party Risk | RELEASE | Release and Deployment Evidence | Evidence request for Business Risk control review | Data Governance | Under IA Review | Under IA Review | Low | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Lee Lead | IAM Ops | Business Risk |  |  |  | 1
ITOPS26-VM-INVENT-005 | Original | Parent |  | VM | Vulnerability Management | INVENT | Asset or Account Inventory | Evidence request for Compliance control review | Vendor Risk | Open | Open | Medium | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Lee Lead | Vendor Risk | Technology Risk |  |  |  | 0
ITOPS26-IR-CHANGE-006 | Original | Parent |  | IR | Incident Response | CHANGE | Change Population | Evidence request for Compliance control review | Platform Eng | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Val Viewer | IAM Ops | Compliance | Y |  |  | 1
ITOPS26-AI-EXCEPTION-007 | Original | Parent |  | AI | Artificial Intelligence | EXCEPTION | Exception, Waiver, or Risk Acceptance | Evidence request for Compliance control review | Vendor Risk | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Morgan Manager | IAM Ops | Technology Risk |  |  |  | 0
ITOPS26-DATA-DOC-008 | Original | Parent |  | DATA | Data Management | DOC | Policies / Procedures / Standards | Evidence request for Compliance control review | Vendor Risk | Closed - Complete | Closed - Complete | Low | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Leadership | Platform Eng | Business Risk | N |  |  | 0
ITOPS26-IR-MONITOR-009 | Original | Parent |  | IR | Incident Response | MONITOR | Monitoring Activities | Evidence request for Compliance control review | Data Governance | Extended | Extended | High | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Leadership | SecOps | Compliance |  |  |  | 0
ITOPS26-VM-SAMPLE-010 | Original | Parent |  | VM | Vulnerability Management | SAMPLE | Sample Selection Evidence | Evidence request for Compliance control review | IAM Ops | Under IA Review | Under IA Review | High | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Sam Auditor | IAM Ops | Compliance |  |  |  | 0
ITOPS26-DR-SAMPLE-011 | Original | Parent |  | DR | Disaster Recovery | SAMPLE | Sample Selection Evidence | Evidence request for Technology Risk control review | Data Governance | Overdue - Extension | Overdue - Extension | Low | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Lee Lead | Data Governance | Technology Risk |  |  |  | 0
ITOPS26-PRIV-INCIDENT-012 | Original | Parent |  | PRIV | Privacy | INCIDENT | Incident Evidence | Evidence request for Technology Risk control review | Data Governance | Overdue | Overdue | High | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test LeadAIC | Vendor Risk | Compliance |  |  |  | 0
ITOPS26-BCP-ATTEST-013 | Original | Parent |  | BCP | Business Continuity | ATTEST | Management Attestation / Certification | Evidence request for Business Risk control review | SecOps | Cancelled | Overdue | Medium | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Leadership | Vendor Risk | Technology Risk |  |  |  | 1
ITOPS26-BCP-CONTRACT-014 | Original | Parent |  | BCP | Business Continuity | CONTRACT | Contractual Documentation | Evidence request for Compliance control review | SecOps | Extended | Extended | Medium | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Logan Leadership | Data Governance | Technology Risk |  |  |  | 1
ITOPS26-SEC-INVENT-015 | Original | Parent |  | SEC | Security | INVENT | Asset or Account Inventory | Evidence request for Business Risk control review | Vendor Risk | Open | Open | High | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Avery Admin | Platform Eng | Business Risk |  |  |  | 0
ITOPS26-DATA-EXCEPTION-016 | Original | Parent |  | DATA | Data Management | EXCEPTION | Exception, Waiver, or Risk Acceptance | Evidence request for Business Risk control review | Vendor Risk | Not Yet Requested | Not Yet Requested | Low | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test Viewer | SecOps | Compliance |  |  |  | 1
ITOPS26-PRIV-ASSESS-017 | Original | Parent |  | PRIV | Privacy | ASSESS | Assessment Results | Evidence request for Compliance control review | SecOps | Closed - Complete | Closed - Complete | Low | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Val Viewer | Platform Eng | Compliance | Y |  |  | 0
ITOPS26-SEC-TRAN-018 | Original | Parent |  | SEC | Security | TRAN | Transaction Support Evidence | Evidence request for Business Risk control review | Data Governance | Not Yet Requested | Not Yet Requested | Medium | [5 empty] | No | 0 | Val Viewer | IAM Ops | Business Risk |  |  |  | 1
ITOPS26-VEND-TRAN-019 | Original | Parent |  | VEND | Third-Party Risk | TRAN | Transaction Support Evidence | Evidence request for Compliance control review | Platform Eng | Overdue - Extension | Overdue - Extension | Low | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Sam Auditor | Platform Eng | Technology Risk |  |  |  | 0
ITOPS26-AC-INVENT-020 | Original | Parent |  | AC | Access Control | INVENT | Asset or Account Inventory | Evidence request for Business Risk control review | Platform Eng | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Admin | Data Governance | Business Risk |  |  |  | 0
ITOPS26-BCP-SAMPLE-021 | Original | Parent |  | BCP | Business Continuity | SAMPLE | Sample Selection Evidence | Evidence request for Technology Risk control review | SecOps | Closed - Complete | Closed - Complete | Low | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Sam Auditor | Vendor Risk | Business Risk | N |  |  | 1
ITOPS26-PRIV-APPROVAL-022 | Original | Parent |  | PRIV | Privacy | APPROVAL | Access / Change Approval Evidence | Evidence request for Technology Risk control review | Data Governance | Overdue | Overdue | Medium | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test LeadAIC | IAM Ops | Business Risk |  |  |  | 0
ITOPS26-VM-RACI-023 | Original | Parent |  | VM | Vulnerability Management | RACI | Roles and Responsibilities | Evidence request for Business Risk control review | Vendor Risk | Under IA Review | Under IA Review | Medium | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Manager | SecOps | Business Risk |  |  |  | 1
ITOPS26-CHG-CHANGE-024 | Original | Parent |  | CHG | Change Management | CHANGE | Change Population | Evidence request for Business Risk control review | Platform Eng | Not Yet Requested | Not Yet Requested | Medium | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Avery Admin | Platform Eng | Business Risk |  |  |  | 0
ITOPS26-SEC-TRAIN-025 | Original | Parent |  | SEC | Security | TRAIN | Training Evidence | Evidence request for Compliance control review | Data Governance | Not Yet Requested | Not Yet Requested | Medium | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Morgan Manager | IAM Ops | Business Risk |  |  |  | 0
ITOPS26-BCP-TRAIN-026 | Original | Parent |  | BCP | Business Continuity | TRAIN | Training Evidence | Evidence request for Compliance control review | Platform Eng | Closed - Complete | Closed - Complete | Low | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Sam Auditor | IAM Ops | Business Risk | N |  |  | 0
ITOPS26-VM-TRAIN-027 | Original | Parent |  | VM | Vulnerability Management | TRAIN | Training Evidence | Evidence request for Compliance control review | SecOps | Overdue | Overdue | Low | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Viewer | SecOps | Business Risk |  |  |  | 1
ITOPS26-APP-TICKET-028 | Original | Parent |  | APP | Application Controls | TICKET | Workflow / Ticket Evidence | Evidence request for Technology Risk control review | SecOps | Open | Open | Medium | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Leadership | Vendor Risk | Compliance |  |  |  | 1
ITOPS26-PRIV-INCIDENT-029 | Original | Parent |  | PRIV | Privacy | INCIDENT | Incident Evidence | Evidence request for Compliance control review | Platform Eng | Extended | Extended | High | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Avery Admin | Data Governance | Business Risk |  |  |  | 0
ITOPS26-VM-TICKET-030 | Original | Parent |  | VM | Vulnerability Management | TICKET | Workflow / Ticket Evidence | Evidence request for Technology Risk control review | IAM Ops | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Test Leadership | Vendor Risk | Technology Risk |  |  |  | 1
ITOPS26-CHG-TEST-031 | Original | Parent |  | CHG | Change Management | TEST | Testing Evidence | Evidence request for Compliance control review | Vendor Risk | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Lee Lead | IAM Ops | Compliance |  |  |  | 0
ITOPS26-OPS-ISSUE-032 | Original | Parent |  | OPS | Operations | ISSUE | Issue Management Evidence | Evidence request for Compliance control review | Vendor Risk | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Auditor | IAM Ops | Business Risk | Y |  |  | 0
ITOPS26-OPS-REVIEW-033 | Original | Parent |  | OPS | Operations | REVIEW | Periodic Review Evidence | Evidence request for Business Risk control review | IAM Ops | Cancelled | Overdue | Medium | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Sam Auditor | IAM Ops | Technology Risk |  |  |  | 1
ITOPS26-GOV-ASSESS-034 | Original | Parent |  | GOV | Governance | ASSESS | Assessment Results | Evidence request for Business Risk control review | Vendor Risk | Under IA Review | Under IA Review | Medium | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Avery Admin | Platform Eng | Compliance |  |  |  | 0
ITOPS26-IR-DATAFLOW-035 | Original | Parent |  | IR | Incident Response | DATAFLOW | Data Flow Evidence | Evidence request for Technology Risk control review | Vendor Risk | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test Viewer | SecOps | Business Risk |  |  |  | 0
ITOPS26-IR-LOG-036 | Original | Parent |  | IR | Incident Response | LOG | Logs / Monitoring Evidence | Evidence request for Technology Risk control review | IAM Ops | Open | Open | High | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Viewer | Platform Eng | Technology Risk |  |  |  | 0
ITOPS26-DATA-DATAFLOW-037 | Original | Parent |  | DATA | Data Management | DATAFLOW | Data Flow Evidence | Evidence request for Business Risk control review | Platform Eng | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Test Leadership | SecOps | Business Risk |  |  |  | 0
ITOPS26-BCP-SOC-038 | Original | Parent |  | BCP | Business Continuity | SOC | Independent Assurance Reports | Evidence request for Compliance control review | Vendor Risk | Extended | Extended | High | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Leadership | Vendor Risk | Technology Risk |  |  |  | 0
ITOPS26-DATA-REMED-039 | Original | Parent |  | DATA | Data Management | REMED | Remediation / Issue Tracking | Evidence request for Technology Risk control review | Vendor Risk | Under IA Review | Under IA Review | Low | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Avery Admin | Platform Eng | Business Risk |  |  |  | 1
ITOPS26-IR-SOC-040 | Original | Parent |  | IR | Incident Response | SOC | Independent Assurance Reports | Evidence request for Compliance control review | IAM Ops | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Morgan Manager | Data Governance | Compliance |  |  |  | 0
ITOPS26-DR-REMED-041 | Original | Parent |  | DR | Disaster Recovery | REMED | Remediation / Issue Tracking | Evidence request for Compliance control review | Vendor Risk | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Auditor | SecOps | Compliance | N |  |  | 0
ITOPS26-VM-APPROVAL-042 | Original | Parent |  | VM | Vulnerability Management | APPROVAL | Access / Change Approval Evidence | Evidence request for Compliance control review | Platform Eng | Overdue | Overdue | Low | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Auditor | Data Governance | Technology Risk |  |  |  | 1
ITOPS26-DR-ASSESS-043 | Original | Parent |  | DR | Disaster Recovery | ASSESS | Assessment Results | Evidence request for Business Risk control review | SecOps | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Avery Admin | SecOps | Technology Risk | Y |  |  | 0
ITOPS26-BCP-TICKET-044 | Original | Parent |  | BCP | Business Continuity | TICKET | Workflow / Ticket Evidence | Evidence request for Business Risk control review | SecOps | Open | Open | Low | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Morgan Manager | SecOps | Technology Risk |  |  |  | 1
ITOPS26-PRIV-SAMPLE-045 | Original | Parent |  | PRIV | Privacy | SAMPLE | Sample Selection Evidence | Evidence request for Technology Risk control review | Vendor Risk | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Sam Auditor | IAM Ops | Compliance |  |  |  | 1
ITOPS26-SEC-ISSUE-046 | Original | Parent |  | SEC | Security | ISSUE | Issue Management Evidence | Evidence request for Business Risk control review | SecOps | Not Yet Requested | Not Yet Requested | Medium | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Val Viewer | Platform Eng | Compliance |  |  |  | 0
ITOPS26-CHG-ASSESS-047 | Original | Parent |  | CHG | Change Management | ASSESS | Assessment Results | Evidence request for Business Risk control review | Data Governance | Cancelled | Overdue | Medium | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Logan Leadership | Platform Eng | Technology Risk |  |  |  | 1
ITOPS26-OPS-CHANGE-048 | Original | Parent |  | OPS | Operations | CHANGE | Change Population | Evidence request for Technology Risk control review | Vendor Risk | Overdue | Overdue | High | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Avery Admin | IAM Ops | Business Risk |  |  |  | 0
ITOPS26-INF-DOC-049 | Original | Parent |  | INF | Infrastructure | DOC | Policies / Procedures / Standards | Evidence request for Technology Risk control review | SecOps | Under IA Review | Under IA Review | Low | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Sam Auditor | SecOps | Compliance |  |  |  | 0
ITOPS26-PRIV-INCIDENT-050 | Original | Parent |  | PRIV | Privacy | INCIDENT | Incident Evidence | Evidence request for Compliance control review | SecOps | Extended | Extended | High | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Leadership | Platform Eng | Compliance |  |  |  | 1
ITOPS26-OPS-CONTRACT-051 | Original | Parent |  | OPS | Operations | CONTRACT | Contractual Documentation | Evidence request for Business Risk control review | Vendor Risk | Overdue - Extension | Overdue - Extension | Low | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Lee Lead | Data Governance | Compliance |  |  |  | 1
ITOPS26-VM-TEST-052 | Original | Parent |  | VM | Vulnerability Management | TEST | Testing Evidence | Evidence request for Business Risk control review | SecOps | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Val Viewer | Vendor Risk | Business Risk | Y |  |  | 1
ITOPS26-CHG-DOC-053 | Original | Parent |  | CHG | Change Management | DOC | Policies / Procedures / Standards | Evidence request for Technology Risk control review | Platform Eng | Under IA Review | Under IA Review | High | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Lee Lead | IAM Ops | Technology Risk |  |  |  | 1
ITOPS26-GOV-TRAN-054 | Original | Parent |  | GOV | Governance | TRAN | Transaction Support Evidence | Evidence request for Business Risk control review | Data Governance | Closed - Complete | Closed - Complete | Low | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Admin | Vendor Risk | Business Risk | N |  |  | 0
ITOPS26-OPS-MONITOR-055 | Original | Parent |  | OPS | Operations | MONITOR | Monitoring Activities | Evidence request for Compliance control review | Data Governance | Cancelled | Overdue | Medium | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Avery Admin | IAM Ops | Compliance |  |  |  | 0
ITOPS26-BCP-CONTRACT-014.1 | Clarification | Child | ITOPS26-BCP-CONTRACT-014 |  |  |  | Contractual Documentation | Follow-up on the original submission |  | Overdue | Overdue | Medium | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Avery Admin | [5 empty] | 0
ITOPS26-VM-APPROVAL-042.1 | Remediation | Child | ITOPS26-VM-APPROVAL-042 |  |  |  | Access / Change Approval Evidence | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | Low | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Avery Admin | [5 empty] | 0
ITOPS26-DATA-EXCEPTION-016.1 | Follow-Up | Child | ITOPS26-DATA-EXCEPTION-016 |  |  |  | Exception, Waiver, or Risk Acceptance | Follow-up on the original submission |  | Open | Open | High | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test LeadAIC | [5 empty] | 0
ITOPS26-PRIV-INCIDENT-050.1 | Remediation | Child | ITOPS26-PRIV-INCIDENT-050 |  |  |  | Incident Evidence | Follow-up on the original submission |  | Under IA Review | Under IA Review | Medium | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Avery Admin | [5 empty] | 0
ITOPS26-VM-TRAIN-027.1 | Follow-Up | Child | ITOPS26-VM-TRAIN-027 |  |  |  | Training Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Leadership |  |  | N |  |  | 0
ITOPS26-VM-TEST-052.1 | Clarification | Child | ITOPS26-VM-TEST-052 |  |  |  | Testing Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Auditor |  |  | N |  |  | 0
ITOPS26-BCP-SAMPLE-021.1 | Clarification | Child | ITOPS26-BCP-SAMPLE-021 |  |  |  | Sample Selection Evidence | Follow-up on the original submission |  | Overdue - Extension | Overdue - Extension | Medium | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test LeadAIC | [5 empty] | 0
ITOPS26-BCP-TICKET-044.1 | Follow-Up | Child | ITOPS26-BCP-TICKET-044 |  |  |  | Workflow / Ticket Evidence | Follow-up on the original submission |  | Overdue - Extension | Overdue - Extension | Low | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test Leadership | [5 empty] | 0
ITOPS26-VEND-RELEASE-004.1 | Remediation | Child | ITOPS26-VEND-RELEASE-004 |  |  |  | Release and Deployment Evidence | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | Medium | [5 empty] | No | 0 | Test Viewer | [5 empty] | 0
ITOPS26-CHG-DOC-053.1 | Follow-Up | Child | ITOPS26-CHG-DOC-053 |  |  |  | Policies / Procedures / Standards | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Viewer |  |  | Y |  |  | 0
ITOPS26-APP-TICKET-028.1 | Clarification | Child | ITOPS26-APP-TICKET-028 |  |  |  | Workflow / Ticket Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Viewer |  |  | Y |  |  | 0
ITOPS26-BCP-ATTEST-013.1 | Clarification | Child | ITOPS26-BCP-ATTEST-013 |  |  |  | Management Attestation / Certification | Follow-up on the original submission |  | Under IA Review | Under IA Review | Low | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Leadership | [5 empty] | 0
ITOPS26-OPS-CONTRACT-051.1 | Remediation | Child | ITOPS26-OPS-CONTRACT-051 |  |  |  | Contractual Documentation | Follow-up on the original submission |  | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Leadership | [5 empty] | 0
ITOPS26-VM-TICKET-030.1 | Follow-Up | Child | ITOPS26-VM-TICKET-030 |  |  |  | Workflow / Ticket Evidence | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Test LeadAIC | [5 empty] | 0
ITOPS26-VM-RACI-023.1 | Follow-Up | Child | ITOPS26-VM-RACI-023 |  |  |  | Roles and Responsibilities | Follow-up on the original submission |  | Extended | Extended | Medium | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Morgan Manager | [5 empty] | 0
ITOPS26-IR-CHANGE-006.1 | Clarification | Child | ITOPS26-IR-CHANGE-006 |  |  |  | Change Population | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Val Viewer | [5 empty] | 0
ITOPS26-PRIV-SAMPLE-045.1 | Follow-Up | Child | ITOPS26-PRIV-SAMPLE-045 |  |  |  | Sample Selection Evidence | Follow-up on the original submission |  | Overdue | Overdue | Medium | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Auditor | [5 empty] | 0
ITOPS26-SEC-TRAN-018.1 | Follow-Up | Child | ITOPS26-SEC-TRAN-018 |  |  |  | Transaction Support Evidence | Follow-up on the original submission |  | Under IA Review | Under IA Review | Low | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Lee Lead | [5 empty] | 0
ITOPS26-DATA-REMED-039.1 | Remediation | Child | ITOPS26-DATA-REMED-039 |  |  |  | Remediation / Issue Tracking | Follow-up on the original submission |  | Open | Open | Medium | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Avery Admin | [5 empty] | 0
ITOPS26-OPS-REVIEW-033.1 | Follow-Up | Child | ITOPS26-OPS-REVIEW-033 |  |  |  | Periodic Review Evidence | Follow-up on the original submission |  | Cancelled | Overdue | High | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Leadership | [5 empty] | 0
ITOPS26-CHG-ASSESS-047.1 | Follow-Up | Child | ITOPS26-CHG-ASSESS-047 |  |  |  | Assessment Results | Follow-up on the original submission |  | Extended | Extended | Low | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Viewer | [5 empty] | 0