## SDLC26 DRL
DRL ID | Request Type | Level | Parent DRL ID | Domain | Domain Name | Pattern | Evidence Type | Requested Item | Control Topic | Status | Status (Auto) | Priority | Date Requested | Due Date | Date Received | Date Closed | Days Open | Received Late | Extension (days) | Auditor | Auditee Owner | BU / Risk Team | Evidence Accepted | Evidence Link | IA Comments | # Follow-Ups
SDLC26-DR-CHANGE-001 | Original | Parent |  | DR | Disaster Recovery | CHANGE | Change Population | Evidence request for Technology Risk control review | SecOps | Not Yet Requested | Not Yet Requested | Low | [5 empty] | No | 0 | Morgan Manager | SecOps | Compliance |  |  |  | 1
SDLC26-DATA-ATTEST-002 | Original | Parent |  | DATA | Data Management | ATTEST | Management Attestation / Certification | Evidence request for Technology Risk control review | Platform Eng | Not Yet Requested | Not Yet Requested | Low | [5 empty] | No | 0 | Test Viewer | Data Governance | Compliance |  |  |  | 0
SDLC26-OPS-CHANGE-003 | Original | Parent |  | OPS | Operations | CHANGE | Change Population | Evidence request for Technology Risk control review | SecOps | Open | Open | High | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Logan Leadership | Data Governance | Business Risk |  |  |  | 0
SDLC26-AC-LIST-004 | Original | Parent |  | AC | Access Control | LIST | System-Generated Population Listing | Evidence request for Compliance control review | IAM Ops | Cancelled | Overdue | High | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Val Viewer | Platform Eng | Technology Risk |  |  |  | 1
SDLC26-OPS-ISSUE-005 | Original | Parent |  | OPS | Operations | ISSUE | Issue Management Evidence | Evidence request for Business Risk control review | Platform Eng | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Admin | Data Governance | Business Risk | Y |  |  | 0
SDLC26-AI-DOC-006 | Original | Parent |  | AI | Artificial Intelligence | DOC | Policies / Procedures / Standards | Evidence request for Business Risk control review | IAM Ops | Overdue | Overdue | Medium | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Admin | Vendor Risk | Technology Risk |  |  |  | 0
SDLC26-IR-DATAFLOW-007 | Original | Parent |  | IR | Incident Response | DATAFLOW | Data Flow Evidence | Evidence request for Business Risk control review | SecOps | Under IA Review | Under IA Review | High | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Leadership | Vendor Risk | Business Risk |  |  |  | 0
SDLC26-INF-REVIEW-008 | Original | Parent |  | INF | Infrastructure | REVIEW | Periodic Review Evidence | Evidence request for Business Risk control review | SecOps | Extended | Extended | Low | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Logan Leadership | Platform Eng | Compliance |  |  |  | 0
SDLC26-CLOUD-CONFIGTEST-009 | Original | Parent |  | CLOUD | Cloud Controls | CONFIGTEST | Configuration Validation Evidence | Evidence request for Technology Risk control review | Vendor Risk | Under IA Review | Under IA Review | Low | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Viewer | Vendor Risk | Technology Risk |  |  |  | 0
SDLC26-IR-APPROVAL-010 | Original | Parent |  | IR | Incident Response | APPROVAL | Access / Change Approval Evidence | Evidence request for Technology Risk control review | SecOps | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Morgan Manager | Platform Eng | Business Risk | N |  |  | 1
SDLC26-AC-CONFIGTEST-011 | Original | Parent |  | AC | Access Control | CONFIGTEST | Configuration Validation Evidence | Evidence request for Compliance control review | Data Governance | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test Admin | SecOps | Technology Risk |  |  |  | 0
SDLC26-AC-SAMPLE-012 | Original | Parent |  | AC | Access Control | SAMPLE | Sample Selection Evidence | Evidence request for Compliance control review | Data Governance | Overdue - Extension | Overdue - Extension | Medium | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test Leadership | Data Governance | Technology Risk |  |  |  | 1
SDLC26-VEND-MONITOR-013 | Original | Parent |  | VEND | Third-Party Risk | MONITOR | Monitoring Activities | Evidence request for Compliance control review | IAM Ops | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Leadership | Vendor Risk | Business Risk | N |  |  | 1
SDLC26-SEC-TRAIN-014 | Original | Parent |  | SEC | Security | TRAIN | Training Evidence | Evidence request for Technology Risk control review | Vendor Risk | Closed - Complete | Closed - Complete | Low | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Val Viewer | Vendor Risk | Business Risk | Y |  |  | 0
SDLC26-CLOUD-CHANGE-015 | Original | Parent |  | CLOUD | Cloud Controls | CHANGE | Change Population | Evidence request for Compliance control review | Platform Eng | Overdue | Overdue | Low | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Viewer | Data Governance | Technology Risk |  |  |  | 1
SDLC26-CHG-TRAN-016 | Original | Parent |  | CHG | Change Management | TRAN | Transaction Support Evidence | Evidence request for Compliance control review | Platform Eng | Not Yet Requested | Not Yet Requested | Low | [5 empty] | No | 0 | Avery Admin | Platform Eng | Compliance |  |  |  | 1
SDLC26-SEC-SAMPLE-017 | Original | Parent |  | SEC | Security | SAMPLE | Sample Selection Evidence | Evidence request for Business Risk control review | SecOps | Under IA Review | Under IA Review | Medium | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Val Viewer | Data Governance | Business Risk |  |  |  | 1
SDLC26-CLOUD-TRAIN-018 | Original | Parent |  | CLOUD | Cloud Controls | TRAIN | Training Evidence | Evidence request for Compliance control review | Vendor Risk | Open | Open | High | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Lee Lead | Platform Eng | Compliance |  |  |  | 0
SDLC26-AC-PERF-019 | Original | Parent |  | AC | Access Control | PERF | Reperformance Evidence | Evidence request for Compliance control review | IAM Ops | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Test Leadership | IAM Ops | Compliance |  |  |  | 0
SDLC26-AC-CONFIGTEST-020 | Original | Parent |  | AC | Access Control | CONFIGTEST | Configuration Validation Evidence | Evidence request for Business Risk control review | Data Governance | Not Yet Requested | Not Yet Requested | Medium | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test Leadership | Data Governance | Business Risk |  |  |  | 0
SDLC26-VM-ATTEST-021 | Original | Parent |  | VM | Vulnerability Management | ATTEST | Management Attestation / Certification | Evidence request for Technology Risk control review | Platform Eng | Extended | Extended | Low | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Manager | Data Governance | Compliance |  |  |  | 1
SDLC26-AC-INCIDENT-022 | Original | Parent |  | AC | Access Control | INCIDENT | Incident Evidence | Evidence request for Business Risk control review | Vendor Risk | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Manager | SecOps | Business Risk |  |  |  | 0
SDLC26-BCP-RACI-023 | Original | Parent |  | BCP | Business Continuity | RACI | Roles and Responsibilities | Evidence request for Business Risk control review | Data Governance | Cancelled | Overdue | Medium | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Auditor | Data Governance | Compliance |  |  |  | 0
SDLC26-VM-LOG-024 | Original | Parent |  | VM | Vulnerability Management | LOG | Logs / Monitoring Evidence | Evidence request for Business Risk control review | SecOps | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test LeadAIC | Vendor Risk | Technology Risk |  |  |  | 0
SDLC26-OPS-TRAN-025 | Original | Parent |  | OPS | Operations | TRAN | Transaction Support Evidence | Evidence request for Technology Risk control review | Data Governance | Overdue | Overdue | High | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Auditor | Data Governance | Business Risk |  |  |  | 0
SDLC26-DR-ATTEST-026 | Original | Parent |  | DR | Disaster Recovery | ATTEST | Management Attestation / Certification | Evidence request for Compliance control review | Data Governance | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Avery Admin | Vendor Risk | Business Risk |  |  |  | 1
SDLC26-IR-REMED-027 | Original | Parent |  | IR | Incident Response | REMED | Remediation / Issue Tracking | Evidence request for Technology Risk control review | SecOps | Under IA Review | Under IA Review | Low | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Avery Admin | IAM Ops | Compliance |  |  |  | 0
SDLC26-CLOUD-DATAFLOW-028 | Original | Parent |  | CLOUD | Cloud Controls | DATAFLOW | Data Flow Evidence | Evidence request for Technology Risk control review | SecOps | Open | Open | Medium | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Leadership | Data Governance | Technology Risk |  |  |  | 1
SDLC26-GOV-REVIEW-029 | Original | Parent |  | GOV | Governance | REVIEW | Periodic Review Evidence | Evidence request for Technology Risk control review | SecOps | Overdue - Extension | Overdue - Extension | Low | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Val Viewer | Platform Eng | Technology Risk |  |  |  | 0
SDLC26-OPS-REMED-030 | Original | Parent |  | OPS | Operations | REMED | Remediation / Issue Tracking | Evidence request for Business Risk control review | Platform Eng | Under IA Review | Under IA Review | High | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Val Viewer | Platform Eng | Technology Risk |  |  |  | 1
SDLC26-CLOUD-MONITOR-031 | Original | Parent |  | CLOUD | Cloud Controls | MONITOR | Monitoring Activities | Evidence request for Technology Risk control review | Platform Eng | Extended | Extended | Medium | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Sam Auditor | Platform Eng | Business Risk |  |  |  | 1
SDLC26-PRIV-INVENT-032 | Original | Parent |  | PRIV | Privacy | INVENT | Asset or Account Inventory | Evidence request for Technology Risk control review | Data Governance | Cancelled | Overdue | Low | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test Leadership | Vendor Risk | Business Risk |  |  |  | 0
SDLC26-SEC-RELEASE-033 | Original | Parent |  | SEC | Security | RELEASE | Release and Deployment Evidence | Evidence request for Technology Risk control review | SecOps | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test LeadAIC | Platform Eng | Business Risk |  |  |  | 0
SDLC26-CLOUD-REMED-034 | Original | Parent |  | CLOUD | Cloud Controls | REMED | Remediation / Issue Tracking | Evidence request for Business Risk control review | Data Governance | Closed - Complete | Closed - Complete | Low | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test LeadAIC | Platform Eng | Compliance | N |  |  | 1
SDLC26-VM-LIST-035 | Original | Parent |  | VM | Vulnerability Management | LIST | System-Generated Population Listing | Evidence request for Technology Risk control review | IAM Ops | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Leadership | Platform Eng | Compliance | Y |  |  | 1
SDLC26-CLOUD-SAMPLE-036 | Original | Parent |  | CLOUD | Cloud Controls | SAMPLE | Sample Selection Evidence | Evidence request for Compliance control review | Data Governance | Open | Open | Medium | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Sam Auditor | IAM Ops | Compliance |  |  |  | 1
SDLC26-CLOUD-APPROVAL-037 | Original | Parent |  | CLOUD | Cloud Controls | APPROVAL | Access / Change Approval Evidence | Evidence request for Technology Risk control review | Vendor Risk | Overdue - Extension | Overdue - Extension | Low | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Logan Leadership | Platform Eng | Compliance |  |  |  | 0
SDLC26-VM-RACI-038 | Original | Parent |  | VM | Vulnerability Management | RACI | Roles and Responsibilities | Evidence request for Business Risk control review | Data Governance | Not Yet Requested | Not Yet Requested | Medium | [5 empty] | No | 0 | Test Viewer | SecOps | Compliance |  |  |  | 0
SDLC26-IR-EXCEPTION-039 | Original | Parent |  | IR | Incident Response | EXCEPTION | Exception, Waiver, or Risk Acceptance | Evidence request for Business Risk control review | Platform Eng | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test Manager | Platform Eng | Technology Risk |  |  |  | 1
SDLC26-DR-CONFIG-040 | Original | Parent |  | DR | Disaster Recovery | CONFIG | Configuration Population | Evidence request for Technology Risk control review | SecOps | Open | Open | Medium | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Lee Lead | SecOps | Compliance |  |  |  | 0
SDLC26-OPS-TICKET-041 | Original | Parent |  | OPS | Operations | TICKET | Workflow / Ticket Evidence | Evidence request for Technology Risk control review | SecOps | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Sam Auditor | SecOps | Technology Risk | Y |  |  | 0
SDLC26-AI-SAMPLE-042 | Original | Parent |  | AI | Artificial Intelligence | SAMPLE | Sample Selection Evidence | Evidence request for Business Risk control review | Vendor Risk | Cancelled | Overdue | Medium | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Lee Lead | SecOps | Compliance |  |  |  | 0
SDLC26-APP-LIST-043 | Original | Parent |  | APP | Application Controls | LIST | System-Generated Population Listing | Evidence request for Compliance control review | IAM Ops | Overdue | Overdue | Medium | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Val Viewer | SecOps | Business Risk |  |  |  | 1
SDLC26-SEC-CONTRACT-044 | Original | Parent |  | SEC | Security | CONTRACT | Contractual Documentation | Evidence request for Compliance control review | Vendor Risk | Under IA Review | Under IA Review | High | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Test Manager | Platform Eng | Business Risk |  |  |  | 1
SDLC26-AC-TEST-045 | Original | Parent |  | AC | Access Control | TEST | Testing Evidence | Evidence request for Compliance control review | Platform Eng | Extended | Extended | High | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Auditor | SecOps | Business Risk |  |  |  | 0
SDLC26-APP-REVIEW-046 | Original | Parent |  | APP | Application Controls | REVIEW | Periodic Review Evidence | Evidence request for Business Risk control review | Platform Eng | Under IA Review | Under IA Review | Low | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Auditor | Platform Eng | Business Risk |  |  |  | 1
SDLC26-APP-MONITOR-047 | Original | Parent |  | APP | Application Controls | MONITOR | Monitoring Activities | Evidence request for Business Risk control review | Data Governance | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Logan Leadership | IAM Ops | Business Risk | N |  |  | 0
SDLC26-AI-LOG-048 | Original | Parent |  | AI | Artificial Intelligence | LOG | Logs / Monitoring Evidence | Evidence request for Technology Risk control review | IAM Ops | Overdue | Overdue | Medium | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Admin | Platform Eng | Technology Risk |  |  |  | 1
SDLC26-APP-RELEASE-049 | Original | Parent |  | APP | Application Controls | RELEASE | Release and Deployment Evidence | Evidence request for Compliance control review | Vendor Risk | Extended | Extended | Medium | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Leadership | Vendor Risk | Technology Risk |  |  |  | 0
SDLC26-AI-INVENT-050 | Original | Parent |  | AI | Artificial Intelligence | INVENT | Asset or Account Inventory | Evidence request for Compliance control review | Platform Eng | Cancelled | Overdue | Low | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Test LeadAIC | Vendor Risk | Technology Risk |  |  |  | 1
SDLC26-APP-CONFIG-051 | Original | Parent |  | APP | Application Controls | CONFIG | Configuration Population | Evidence request for Business Risk control review | Vendor Risk | Under IA Review | Under IA Review | Medium | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Sam Auditor | Data Governance | Technology Risk |  |  |  | 0
SDLC26-CHG-CONFIGTEST-052 | Original | Parent |  | CHG | Change Management | CONFIGTEST | Configuration Validation Evidence | Evidence request for Compliance control review | Data Governance | Overdue - Extension | Overdue - Extension | Low | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Avery Admin | IAM Ops | Business Risk |  |  |  | 0
SDLC26-CLOUD-ASSESS-053 | Original | Parent |  | CLOUD | Cloud Controls | ASSESS | Assessment Results | Evidence request for Business Risk control review | IAM Ops | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Test Viewer | SecOps | Compliance | Y |  |  | 0
SDLC26-DATA-TEST-054 | Original | Parent |  | DATA | Data Management | TEST | Testing Evidence | Evidence request for Business Risk control review | Vendor Risk | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Sam Auditor | Vendor Risk | Compliance | N |  |  | 1
SDLC26-VM-TRAIN-055 | Original | Parent |  | VM | Vulnerability Management | TRAIN | Training Evidence | Evidence request for Technology Risk control review | Platform Eng | Under IA Review | Under IA Review | High | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Test Auditor | Data Governance | Business Risk |  |  |  | 0
SDLC26-VM-ATTEST-021.1 | Follow-Up | Child | SDLC26-VM-ATTEST-021 |  |  |  | Management Attestation / Certification | Follow-up on the original submission |  | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Avery Admin | [5 empty] | 0
SDLC26-APP-LIST-043.1 | Remediation | Child | SDLC26-APP-LIST-043 |  |  |  | System-Generated Population Listing | Follow-up on the original submission |  | Overdue - Extension | Overdue - Extension | High | 2026-07-19 | 2026-07-29 |  |  | 40 | No | 3 | Val Viewer | [5 empty] | 0
SDLC26-DR-CHANGE-001.1 | Clarification | Child | SDLC26-DR-CHANGE-001 |  |  |  | Change Population | Follow-up on the original submission |  | Overdue | Overdue | High | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Auditor | [5 empty] | 0
SDLC26-AI-INVENT-050.1 | Follow-Up | Child | SDLC26-AI-INVENT-050 |  |  |  | Asset or Account Inventory | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | Medium | [5 empty] | No | 0 | Sam Auditor | [5 empty] | 0
SDLC26-AC-SAMPLE-012.1 | Remediation | Child | SDLC26-AC-SAMPLE-012 |  |  |  | Sample Selection Evidence | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | Low | [5 empty] | No | 0 | Test Manager | [5 empty] | 0
SDLC26-DR-ATTEST-026.1 | Remediation | Child | SDLC26-DR-ATTEST-026 |  |  |  | Management Attestation / Certification | Follow-up on the original submission |  | Overdue | Overdue | High | 2026-07-29 | 2026-08-05 |  |  | 30 | No | 0 | Test Auditor | [5 empty] | 0
SDLC26-CHG-TRAN-016.1 | Remediation | Child | SDLC26-CHG-TRAN-016 |  |  |  | Transaction Support Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Avery Admin |  |  | Y |  |  | 0
SDLC26-CLOUD-MONITOR-031.1 | Clarification | Child | SDLC26-CLOUD-MONITOR-031 |  |  |  | Monitoring Activities | Follow-up on the original submission |  | Cancelled | Overdue | High | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Logan Leadership | [5 empty] | 0
SDLC26-CLOUD-SAMPLE-036.1 | Remediation | Child | SDLC26-CLOUD-SAMPLE-036 |  |  |  | Sample Selection Evidence | Follow-up on the original submission |  | Extended | Extended | Low | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Morgan Manager | [5 empty] | 0
SDLC26-SEC-SAMPLE-017.1 | Clarification | Child | SDLC26-SEC-SAMPLE-017 |  |  |  | Sample Selection Evidence | Follow-up on the original submission |  | Under IA Review | Under IA Review | Medium | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Lee Lead | [5 empty] | 0
SDLC26-SEC-CONTRACT-044.1 | Remediation | Child | SDLC26-SEC-CONTRACT-044 |  |  |  | Contractual Documentation | Follow-up on the original submission |  | Under IA Review | Under IA Review | High | 2026-08-18 | 2026-08-25 | 2026-08-23 |  | 5 | No | 0 | Lee Lead | [5 empty] | 0
SDLC26-AC-LIST-004.1 | Remediation | Child | SDLC26-AC-LIST-004 |  |  |  | System-Generated Population Listing | Follow-up on the original submission |  | Open | Open | Medium | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Lee Lead | [5 empty] | 0
SDLC26-CLOUD-REMED-034.1 | Follow-Up | Child | SDLC26-CLOUD-REMED-034 |  |  |  | Remediation / Issue Tracking | Follow-up on the original submission |  | Open | Open | High | 2026-08-26 | 2026-09-02 |  |  | 2 | No | 0 | Test Manager | [5 empty] | 0
SDLC26-CLOUD-CHANGE-015.1 | Clarification | Child | SDLC26-CLOUD-CHANGE-015 |  |  |  | Change Population | Follow-up on the original submission |  | Extended | Extended | Medium | 2026-08-26 | 2026-09-10 |  |  | 2 | No | 5 | Test Leadership | [5 empty] | 0
SDLC26-APP-REVIEW-046.1 | Follow-Up | Child | SDLC26-APP-REVIEW-046 |  |  |  | Periodic Review Evidence | Follow-up on the original submission |  | Under IA Review | Under IA Review | Medium | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Avery Admin | [5 empty] | 0
SDLC26-VEND-MONITOR-013.1 | Follow-Up | Child | SDLC26-VEND-MONITOR-013 |  |  |  | Monitoring Activities | Follow-up on the original submission |  | Under IA Review | Under IA Review | High | 2026-07-19 | 2026-07-24 | 2026-08-26 |  | 38 | Yes | 0 | Logan Leadership | [5 empty] | 0
SDLC26-IR-APPROVAL-010.1 | Clarification | Child | SDLC26-IR-APPROVAL-010 |  |  |  | Access / Change Approval Evidence | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Test Manager | [5 empty] | 0
SDLC26-IR-EXCEPTION-039.1 | Clarification | Child | SDLC26-IR-EXCEPTION-039 |  |  |  | Exception, Waiver, or Risk Acceptance | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | High | 2026-07-29 | 2026-08-05 | 2026-08-03 | 2026-08-08 | 10 | No | 0 | Sam Auditor |  |  | Y |  |  | 0
SDLC26-AI-LOG-048.1 | Remediation | Child | SDLC26-AI-LOG-048 |  |  |  | Logs / Monitoring Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | Low | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Leadership |  |  | N |  |  | 0
SDLC26-CLOUD-DATAFLOW-028.1 | Follow-Up | Child | SDLC26-CLOUD-DATAFLOW-028 |  |  |  | Data Flow Evidence | Follow-up on the original submission |  | Closed - Complete | Closed - Complete | Medium | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 15 | Yes | 0 | Test Admin |  |  | N |  |  | 0
SDLC26-DATA-TEST-054.1 | Clarification | Child | SDLC26-DATA-TEST-054 |  |  |  | Testing Evidence | Follow-up on the original submission |  | Cancelled | Overdue | Low | 2026-08-03 | 2026-08-10 |  |  | 25 | No | 0 | Logan Leadership | [5 empty] | 0
SDLC26-OPS-REMED-030.1 | Follow-Up | Child | SDLC26-OPS-REMED-030 |  |  |  | Remediation / Issue Tracking | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | High | [5 empty] | No | 0 | Sam Auditor | [5 empty] | 0
SDLC26-VM-LIST-035.1 | Clarification | Child | SDLC26-VM-LIST-035 |  |  |  | System-Generated Population Listing | Follow-up on the original submission |  | Not Yet Requested | Not Yet Requested | High | 2026-09-02 | 2026-09-10 |  |  | 0 | No | 0 | Morgan Manager | [5 empty] | 0